## Rincian Biaya rev.02 (asuransi)
DETAIL OF DOCKING AND REPAIR COST
Rincian Biaya Docking Dan Perbaikan
Project Information
No |  |  |  | : 20/FIN/MKT-MNB/III/2025 |  |  |  | Name
Type |  |  |  | : All |  |  |  | Length | : 91.44 Meter
Client | [7 empty] | Breadth | : 24.38 Meter
Contact | [7 empty] | Depth | : 5.48 Meter
[8 empty] | Klass | : RINA
No |  |  | Item |  |  | Volume |  | Unit Price | Service | Material
I |  |  | PELAYANAN UMUM | [8 empty] | Luasan Painting
|  | a |  | Docking / Undocking |  | 1 | Ls | 25000000 | 25000000 |  |  | L | 26.98 | 242.82 | 242.82
|  | b |  | Asistensi naik/ turun dock, termasuk persiapan ganjal |  | 1 | Ls | 6500000 | 6500000 |  |  | B | 9 |  |  | #REF! | #REF! | #REF!
|  | c |  | Asistensi dengan mooring Boat |  | 1 | Ls | 5000000 | 5000000 |  |  | D | #REF! | 70
|  | d |  | Sewa dock selama tongkang dalam perbaikan (27 Februari 2025 - 25 Februari 2025) |  | 27 | Hari | 1500000 | 40500000 |  |  | Keliling | 71.96 |  | 19.66 | Panjang Sideboard
|  | e |  | Fasilitas sandar sesudah docking (sewa sandar) (26 Maret 2025 - 8 April 2025) |  | 5 | Hari | 300000 | 1500000 |  |  | Bottom | 197.82 |  | 7 | Lebar Sideboard
|  | f |  | Disediakan Tempat penyimpanan logistik selama perbaikan |  | 1 | Ls | 2000000 | 2000000 |  |  |  | #REF! | #REF! | #REF!
|  | g |  | Penggunaan alat angkat (<1 Ton) |  | 1 | Ls | 9000000 | 9000000 |  |  |  | #REF!
II |  |  | PERAWATAN BADAN KAPAL (Supplai Material by Owner)
|  | a |  | Sandblasting Bottom Sampai Waterline (S.A 2.0) |  | 137 | m2 | 85000 | 11645000
|  | b |  | Sandblasting Top Side (S.A 2.0) |  | 65 | m2 | 85000 | 5525000 |  |  | 1 | PELAYANAN UMUM
|  | c |  | Cuci Air Tawar |  | 202 | m2 | 10000 | 2020000
|  | f |  | Pengecatan Bagian Bawah Air (1x primer,1x sealer,1 xAF) |  | 137 | m2 | 45000 | 6165000 |  |  | 2 | PERAWATAN LAMBUNG
|  | g |  | Pengecatan Top Side (1x primer,1x top coat) |  | 65 | m2 | 30000 | 1950000 |  |  | 4 | SISTIM PENGGERAK
|  | j |  | Pemasangan Zinc Anode |  | 8 | bh | 125000 | 1000000 |  |  | 14 | PERLENGKAPAN DECK
|  | k |  | Pengecatan Draft Mark, Nama Kapal |  | 1 | Ls | 1300000 | 1300000 |  |  | 15 | AKOMODASI
III |  |  | TANGKI - TANGKI
|  | a |  | Buka Manhole |  | 16 | pcs | 200000 | 3200000
|  | b |  | Dilakukan Freegas Sebelum Pemeriksaan Kedalam Tangki |  | 9 | Tank | 250000 | 2250000
|  | c |  | Air Test tangki |  | 11 | Tank | 1700000 | 18700000
IV |  |  | LAPORAN DAN GAMBAR
|  | a |  | Dibuatkan laporan pengedockan dan gambar bukaan kulit sesuai posisi replating |  | 1 | set | 2000000 | 2000000
JR Rev. 00 Initial Survey join with OS (28/02/25)
I |  |  | REPLATTING
| I.1 |  |  | BOTTOM
|  | a |  | Fr 5/6-6/7
|  |  |  | - | Lajur D/E SB ¦ Plate (ABS) thickness 12 mm ¦ 2050 X 1840 mm | 355.3224 | Kg | 48000 |  | 17055475.2
|  |  |  | - | Lajur E SB ¦ Plate (ABS) thickness 12 mm ¦ 2050 X 920 mm | 177.6612 | Kg | 48000 |  | 8527737.6
|  | b |  | Fr 6/7-9/10
|  |  |  | - | Lajur D/E SB ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 1840 mm | 1060.7674 | Kg | 48000 |  | 50916833.28
|  |  |  | - | Lajur E SB ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 920 mm | 530.3837 | Kg | 48000 |  | 25458416.64
|  | c |  | Fr 9/10-12/13
|  |  |  | - | Lajur D/E SB ¦ Plate (ABS) thickness 12 mm ¦ 6100 X 1840 mm | 1057.3008 | Kg | 48000 |  | 50750438.4
|  |  |  | - | Lajur E SB ¦ Plate (ABS) thickness 12 mm ¦ 6100 X 920 mm | 528.6504 | Kg | 48000 |  | 25375219.2
|  | d |  | Fr 12/13-15/16
|  |  |  | - | Lajur D/E SB ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 1840 mm | 1060.7674 | Kg | 48000 |  | 50916833.28
|  |  |  | - | Lajur E SB ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 920 mm | 530.3837 | Kg | 48000 |  | 25458416.64
|  | e |  | Fr 15/16-18/19
|  |  |  | - | Lajur D/E SB ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 1840 mm | 1060.7674 | Kg | 48000 |  | 50916833.28
|  |  |  | - | Lajur E SB ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 920 mm | 530.3837 | Kg | 48000 |  | 25458416.64
|  | f |  | Fr 18/19-20/21
|  |  |  | - | Lajur D SB ¦ Plate (ABS) thickness 12 mm ¦ 3550 X 730 mm | 244.1193 | Kg | 48000 |  | 11717726.4
|  | g |  | Fr 36/37-39/40
|  |  |  | - | Lajur E SB ¦ Plate (ABS) thickness 12 mm ¦ 6720 X 650 mm | 411.4656 | Kg | 48000 |  | 19750348.8
| I.2 |  |  | CHINE
|  | a |  | Fr 5/6-6/7 SB
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 2120 X 810 mm | 161.7602 | Kg | 48000 |  | 7764491.52
|  | b |  | Fr 6/7-10/11 SB
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 6130 X 810 mm | 467.7313 | Kg | 48000 |  | 22451100.48
[8 empty] | Total | 145255000 | 392518287.36 | [6 empty] | 102.15 | Panjang Sideboard
[9 empty] | Service | Material
Say : | [16 empty] | 26.04 | Lebar Sideboard
Note : | [8 empty] | Balikpapan, 19 April 2025
1 |  |  | Cara pembayaran : | [5 empty] | PT. Meranti Nusa Bahari
Aditya Agung H.
General Manager
|  | c |  | Fr 10/11-13/14 SB
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 810 mm | 466.9682 | Kg | 48000 |  | 22414475.52
|  | d |  | Fr 13/14-15/16 SB
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 3360 X 810 mm | 256.3747 | Kg | 48000 |  | 12305986.56
|  | e |  | Fr 15/16-18/19 SB
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 6020 X 810 mm | 459.338 | Kg | 48000 |  | 22048225.92
|  | f |  | Fr 18/19-22/23 SB
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 810 mm | 466.9682 | Kg | 48000 |  | 22414475.52
|  | g |  | Fr 5/6-22/23
|  |  |  | - | Lower chine ¦ Roundbar size. 2" ¦ 29560 mm | 564.3418 | Kg | 48000 |  | 27088405.632
|  |  |  | - | Upper chine ¦ Roundbar size. 2" ¦ 23900 mm | 456.2845 | Kg | 48000 |  | 21901654.08
|  | h |  | Fr 36/37-39/40
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 6110 X 500 mm | 345.3372 | Kg | 48000 |  | 16576185.6
|  |  |  | - | Lower chine ¦ Roundbar size. 2" ¦ 6010 mm | 114.7393 | Kg | 48000 |  | 5507487.072
| I.3 |  |  | SIDE SHELL
|  | a |  | Fr 5/6-8/9 SB
|  |  |  | - | Lajur G ¦ Plate (ABS) thickness 12 mm ¦ 5380 X 930 mm | 471.3203 | Kg | 48000 |  | 22623373.44
|  | b |  | Fr 8/9-12/13 SB
|  |  |  | - | Lajur G ¦ Plate (ABS) thickness 12 mm ¦ 6110 X 930 mm | 535.2727 | Kg | 48000 |  | 25693087.68
|  | c |  | Fr 12/13-15/16 SB
|  |  |  | - | Lajur G ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 930 mm | 536.1487 | Kg | 48000 |  | 25735138.56
|  | d |  | Fr 15/16-18/19 SB
|  |  |  | - | Lajur G ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 930 mm | 536.1487 | Kg | 48000 |  | 25735138.56
|  | e |  | Fr 0/1-1/2 PS
|  |  |  | - | Lajur H ¦ Plate (ABS) thickness 12 mm ¦ 1100 X 1760 mm | 182.3712 | Kg | 48000 |  | 8753817.6
|  |  |  | - | Lajur H/I ¦ Plate (ABS) thickness 12 mm ¦ 1100 X 460 mm | 57.1982 | Kg | 48000 |  | 2745515.52
|  | f |  | Fr 1/2-4/5 PS
|  |  |  | - | Lajur G ¦ Plate (ABS) thickness 12 mm ¦ 3480 X 740 mm | 242.5838 | Kg | 48000 |  | 11644024.32
|  |  |  | - | Lajur G/H ¦ Plate (ABS) thickness 12 mm ¦ 6100 X 1540 mm | 884.9148 | Kg | 48000 |  | 42475910.4
|  |  |  | - | Lajur H/I ¦ Plate (ABS) thickness 12 mm ¦ 6100 X 1760 mm | 1011.3312 | Kg | 48000 |  | 48543897.6
|  | g |  | Fr 4/5-7/8 PS
|  |  |  | - | Lajur G ¦ Plate (ABS) thickness 12 mm ¦ 6100 X 740 mm | 425.2188 | Kg | 48000 |  | 20410502.4
|  |  |  | - | Lajur G/H ¦ Plate (ABS) thickness 12 mm ¦ 6100 X 1540 mm | 884.9148 | Kg | 48000 |  | 42475910.4
|  |  |  | - | Lajur H/I ¦ Plate (ABS) thickness 12 mm ¦ 6100 X 1760 mm | 1011.3312 | Kg | 48000 |  | 48543897.6
|  | h |  | Fr 7/8-10/11 PS
|  |  |  | - | Lajur G/H ¦ Plate (ABS) thickness 12 mm ¦ 6020 X 1830 mm | 1037.7637 | Kg | 48000 |  | 49812658.56
|  | i |  | Fr 0-7/8 PS
|  |  |  | - | Sheer strake (sideshell) ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 1860 mm | 87.606 | Kg | 48000 |  | 4205088
|  |  |  | - | Sheer strake (sideshell) ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 4830 mm | 227.493 | Kg | 48000 |  | 10919664
|  |  |  | - | Sheer strake (sideshell) ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 5360 mm | 252.456 | Kg | 48000 |  | 12117888
|  | j |  | Draft mark AP PS
|  |  |  | - | Letter 2,3,4,5,6,8 ¦ Plate (A) thickness 8 mm ¦ 100 X 80 mm @ 18 sht | 18 | Set | 100000 |  | 1800000
|  |  |  | - | Letter M ¦ Plate (A) thickness 8 mm ¦ 100 X 80 mm @ 4 sht | 4 | Set | 100000 |  | 400000
|  | k |  | Draft mark AP SB
|  |  |  | - | Letter 2,4 ¦ Plate (A) thickness 8 mm ¦ 140 X 90 mm @ 2 sht | 2 | Set | 100000 |  | 200000
| I.4 |  |  | CORNER
|  | a |  | Corner AP
|  |  |  | - | Corner PS ¦ Plate (ABS) thickness 12 mm ¦ 2040 X 1800 mm | 345.9024 | Kg | 48000 |  | 16603315.2
|  |  |  | - | Sheer strake ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 4250 mm | 200.175 | Kg | 48000 |  | 9608400
[8 empty] | Total | 0 | 581304123.744
[9 empty] | Service | Material
Say :
Note : | [8 empty] | Balikpapan, 19 April 2025
1 |  |  | Cara pembayaran : | [5 empty] | PT. Meranti Nusa Bahari
Aditya Agung H.
General Manager
| I.5 |  |  | MAIN DECK
|  | a |  | Fr 0-1/2 PS
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 3580 X 940 mm | 317.0018 | Kg | 48000 |  | 15216088.32
|  | b |  | Fr 1/2-3/4 PS
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 4420 X 940 mm | 391.3822 | Kg | 48000 |  | 18786343.68
| I.6 |  |  | SIDEBOARD
|  | a |  | Sideboard stantion PS
|  |  |  | - | St 1 , web ¦ Plate (A) thickness 10 mm ¦ 600 X 350 mm | 19.782 | Kg | 48000 |  | 949536
|  |  |  | - | St 1 , face ¦ Plate (A) thickness 10 mm ¦ 350 X 100 mm | 3.297 | Kg | 48000 |  | 158256
|  |  |  | - | St 2 , web ¦ Plate (A) thickness 10 mm ¦ 600 X 350 mm | 19.782 | Kg | 48000 |  | 949536
|  |  |  | - | St 2 , face ¦ Plate (A) thickness 10 mm ¦ 350 X 100 mm | 3.297 | Kg | 48000 |  | 158256
|  |  |  | - | St 3 , web ¦ Plate (A) thickness 10 mm ¦ 600 X 350 mm | 19.782 | Kg | 48000 |  | 949536
|  |  |  | - | St 3 , face ¦ Plate (A) thickness 10 mm ¦ 350 X 100 mm | 3.297 | Kg | 48000 |  | 158256
|  |  |  | - | Baseplate ¦ Plate (A) thickness 10 mm ¦ 620 X 70 mm @ 3 sht | 12.2648 | Kg | 48000 |  | 588712.32
| I.8 |  |  | INTERNAL TANK
|  | a |  | Tank 10 PS
|  |  |  | - | TBHD plate ¦ Plate (A) thickness 8 mm ¦ 4150 X 1190 mm | 310.1378 | Kg | 48000 |  | 14886614.4
|  |  |  | - | Ordinary chine ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 750 mm | 35.325 | Kg | 48000 |  | 1695600
|  |  |  | - | Web chine, Web ¦ Plate (A) thickness 10 mm ¦ 500 X 330 mm | 15.543 | Kg | 48000 |  | 746064
|  |  |  | - | Web chine, Web ¦ Plate (A) thickness 10 mm ¦ 500 X 300 mm | 14.13 | Kg | 48000 |  | 678240
|  |  |  | - | Web chine, Face ¦ Plate (A) thickness 10 mm ¦ 190 X 130 mm | 2.3267 | Kg | 48000 |  | 111683.52
|  |  |  | - | Web chine, Face ¦ Plate (A) thickness 10 mm ¦ 120 X 120 mm | 1.3565 | Kg | 48000 |  | 65111.04
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 2980 mm | 67.3718 | Kg | 48000 |  | 3233848.32
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 4820 mm | 108.9706 | Kg | 48000 |  | 5230586.88
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 6130 mm | 138.587 | Kg | 48000 |  | 6652177.92
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 7350 mm | 166.1688 | Kg | 48000 |  | 7976102.4
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 8540 mm | 193.0723 | Kg | 48000 |  | 9267471.36
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9840 mm | 222.4627 | Kg | 48000 |  | 10678210.56
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 430 mm | 9.7214 | Kg | 48000 |  | 466629.12
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 460 mm | 10.3997 | Kg | 48000 |  | 499184.64
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 1280 mm | 28.9382 | Kg | 48000 |  | 1389035.52
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 770 mm | 17.4082 | Kg | 48000 |  | 835591.68
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 1180 mm | 26.6774 | Kg | 48000 |  | 1280517.12
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 670 mm | 15.1474 | Kg | 48000 |  | 727073.28
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 1030 mm | 23.2862 | Kg | 48000 |  | 1117739.52
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 1130 mm | 25.547 | Kg | 48000 |  | 1226257.92
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 880 mm | 19.895 | Kg | 48000 |  | 954961.92
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 950 mm | 21.4776 | Kg | 48000 |  | 1030924.8
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 770 mm | 17.4082 | Kg | 48000 |  | 835591.68
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 3570 mm | 201.7764 | Kg | 48000 |  | 9685267.2
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 3480 mm | 196.6896 | Kg | 48000 |  | 9441100.8
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 2930 mm | 165.6036 | Kg | 48000 |  | 7948972.8
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 2170 mm | 122.6484 | Kg | 48000 |  | 5887123.2
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 1400 mm | 79.128 | Kg | 48000 |  | 3798144
|  |  |  | - | Deck longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 7530 mm | 170.2382 | Kg | 48000 |  | 8171435.52
|  |  |  | - | Deck beam ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 1210 mm @ 5 pcs | 341.946 | Kg | 48000 |  | 16413408
|  |  |  | - | Bracket corner ¦ Plate (A) thickness 10 mm ¦ 920 X 400 mm | 34.6656 | Kg | 48000 |  | 1663948.8
|  |  |  | - | Bracket side shell long. - TBHD ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 420 mm @ 7 pcs | 138.474 | Kg | 48000 |  | 6646752
|  |  |  | - | Bracket side shell long. - web frame ¦ Plate (A) thickness 10 mm ¦ 400 X 250 mm @ 5 sht | 47.1 | Kg | 48000 |  | 2260800
|  |  |  | - | Collar ¦ Plate (A) thickness 8 mm ¦ 180 X 80 mm @ 14 sht | 15.1926 | Kg | 48000 |  | 729243.648
[8 empty] | Total | 0 | 182145933.888
[9 empty] | Service | Material
Say :
Note : | [8 empty] | Balikpapan, 19 April 2025
1 |  |  | Cara pembayaran : | [5 empty] | PT. Meranti Nusa Bahari
Aditya Agung H.
General Manager
|  | b |  | Tank 9 PS
|  |  |  | - | TBHD plate 9/8 ¦ Plate (A) thickness 8 mm ¦ 1970 X 450 mm | 66.8066 | Kg | 48000 |  | 3206718.72
|  |  |  | - | TBHD horizontal stringer ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 3020 mm | 170.6904 | Kg | 48000 |  | 8193139.2
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9040 mm @ 2 pcs | 408.7526 | Kg | 48000 |  | 19620126.72
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 3970 mm @ 1 pcs | 89.7538 | Kg | 48000 |  | 4308180.48
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 8540 mm @ 1 pcs | 193.0723 | Kg | 48000 |  | 9267471.36
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 3480 mm @ 2 pcs | 157.3517 | Kg | 48000 |  | 7552880.64
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 2020 mm | 114.1704 | Kg | 48000 |  | 5480179.2
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 2060 mm | 116.4312 | Kg | 48000 |  | 5588697.6
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 2480 mm | 140.1696 | Kg | 48000 |  | 6728140.8
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 3600 mm | 203.472 | Kg | 48000 |  | 9766656
|  |  |  | - | Bracket side shell long. - stf TBHD 9/10 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 620 mm @ 5 pcs | 146.01 | Kg | 48000 |  | 7008480
|  |  |  | - | Bracket side shell long. - web frame ¦ Plate (A) thickness 10 mm ¦ 400 X 250 mm @ 3 sht | 28.26 | Kg | 48000 |  | 1356480
|  |  |  | - | Bracket side shell long. - TBHD 9/8 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 400 mm @ 3 pcs | 56.52 | Kg | 48000 |  | 2712960
|  |  |  | - | Bracket side shell long. - side stringer ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 620 mm | 35.0424 | Kg | 48000 |  | 1682035.2
|  |  |  | - | Ladder holder bracket ¦ Plate (A) thickness 10 mm ¦ 200 X 90 mm @ 4 sht | 6.7824 | Kg | 48000 |  | 325555.2
|  |  |  | - | Collar ¦ Plate (A) thickness 8 mm ¦ 180 X 80 mm @ 3 sht | 3.2556 | Kg | 48000 |  | 156266.496
|  | c |  | Tank 6 SB
|  |  |  | - | Chine longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 1000 mm | 22.608 | Kg | 48000 |  | 1085184
|  | d |  | Tank 7 SB
|  |  |  | - | TBHD plate 7/6 ¦ Plate (A) thickness 8 mm ¦ 840 X 300 mm | 18.9907 | Kg | 48000 |  | 911554.56
|  |  |  | - | Vertical stf TBHD 7/8 ¦ Angle bar size. 120 x 120 x 10 mm ¦ 780 mm | 17.6342 | Kg | 48000 |  | 846443.52
|  |  |  | - | Diagonal stf TBHD 7/8 ¦ Angle bar size. 120 x 120 x 10 mm ¦ 300 mm | 6.7824 | Kg | 48000 |  | 325555.2
|  |  |  | - | Bottom longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9040 mm | 204.3763 | Kg | 48000 |  | 9810063.36
|  |  |  | - | Bottom longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 7020 mm | 158.7082 | Kg | 48000 |  | 7617991.68
|  |  |  | - | Bottom longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 7140 mm | 161.4211 | Kg | 48000 |  | 7748213.76
|  |  |  | - | Web bottom transverse ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 2060 mm @ 3 pcs | 349.2936 | Kg | 48000 |  | 16766092.8
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 5790 mm | 130.9003 | Kg | 48000 |  | 6283215.36
|  |  |  | - | Chine longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9040 mm | 204.3763 | Kg | 48000 |  | 9810063.36
|  |  |  | - | Web chine, Web ¦ Plate (A) thickness 10 mm ¦ 1430 X 640 mm @ 3 sht | 215.5296 | Kg | 48000 |  | 10345420.8
|  |  |  | - | Web chine, Face ¦ Plate (A) thickness 10 mm ¦ 750 X 100 mm @ 3 sht | 21.195 | Kg | 48000 |  | 1017360
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 1150 mm @ 2 pcs | 129.996 | Kg | 48000 |  | 6239808
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 1130 mm | 63.8676 | Kg | 48000 |  | 3065644.8
|  |  |  | - | Bracket bottom long. - TBHD 7/8 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 500 mm @ 3 pcs | 70.65 | Kg | 48000 |  | 3391200
|  |  |  | - | Bracket bottom long. - vertical stf. TBHD 7/6 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 500 mm | 23.55 | Kg | 48000 |  | 1130400
|  |  |  | - | Bracket bottom long - web bottom trans. ¦ Plate (A) thickness 10 mm ¦ 400 X 250 mm @ 4 sht | 37.68 | Kg | 48000 |  | 1808640
|  |  |  | - | Bracket chine long - web chine ¦ Plate (A) thickness 8 mm ¦ 550 X 300 mm @ 3 sht | 37.3032 | Kg | 48000 |  | 1790553.6
|  |  |  | - | Bracket chine long. - TBHD 7/6 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 400 mm | 18.84 | Kg | 48000 |  | 904320
|  |  |  | - | Bracket chine long. - diagonal stf TBHD 7/8 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 400 mm | 18.84 | Kg | 48000 |  | 904320
|  |  |  | - | Bracket side shell long. - TBHD 7/8 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 600 mm | 28.26 | Kg | 48000 |  | 1356480
|  |  |  | - | Stripping bracket chine ¦ Plate (A) thickness 8 mm ¦ 400 X 90 mm @ 3 sht | 8.1389 | Kg | 48000 |  | 390666.24
|  |  |  | - | Stripping bracket pillar ¦ Plate (A) thickness 8 mm ¦ 400 X 90 mm @ 3 sht | 8.1389 | Kg | 48000 |  | 390666.24
|  |  |  | - | Collar ¦ Plate (A) thickness 8 mm ¦ 180 X 80 mm @ 14 sht | 15.1926 | Kg | 48000 |  | 729243.648
|  |  |  | - | Ladder holder bracket ¦ Plate (A) thickness 8 mm ¦ 180 X 80 mm @ 2 sht | 2.1704 | Kg | 48000 |  | 104177.664
|  | e |  | Tank 8 SB
|  |  |  | - | TBHD plate 8/7 ¦ Plate (A) thickness 8 mm ¦ 2030 X 760 mm | 96.8878 | Kg | 48000 |  | 4650616.32
|  |  |  | - | TBHD plate 8/7 ¦ Plate (A) thickness 8 mm ¦ 550 X 440 mm | 18.2371 | Kg | 48000 |  | 875381.76
|  |  |  | - | Sway ¦ H-beam size. 150 x 150 x 7 x 10 mm ¦ 410 mm | 15.498 | Kg | 48000 |  | 743904
|  |  |  | - | Vertical stf TBHD 8/9 ¦ Angle bar size. 120 x 120 x 10 mm ¦ 430 mm | 9.7214 | Kg | 48000 |  | 466629.12
|  |  |  | - | Vertical stf TBHD 8/9 ¦ Angle bar size. 120 x 120 x 10 mm ¦ 750 mm @ 2 pcs | 33.912 | Kg | 48000 |  | 1627776
|  |  |  | - | Diagonal stf TBHD 8/9 ¦ Angle bar size. 120 x 120 x 10 mm ¦ 600 mm | 13.5648 | Kg | 48000 |  | 651110.4
[8 empty] | Total | 0 | 196742663.808
[9 empty] | Service | Material
Say :
Note : | [8 empty] | Balikpapan, 19 April 2025
1 |  |  | Cara pembayaran : | [5 empty] | PT. Meranti Nusa Bahari
Aditya Agung H.
General Manager
|  |  |  | - | Bottom longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9040 mm @ 3 pcs | 613.129 | Kg | 48000 |  | 29430190.08
|  |  |  | - | Web bottom transverse ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 2050 mm @ 4 pcs | 463.464 | Kg | 48000 |  | 22246272
|  |  |  | - | Chine longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9040 mm | 204.3763 | Kg | 48000 |  | 9810063.36
|  |  |  | - | Web chine, Web ¦ Plate (A) thickness 10 mm ¦ 1480 X 640 mm @ 4 sht | 297.4208 | Kg | 48000 |  | 14276198.4
|  |  |  | - | Web chine, Face ¦ Plate (A) thickness 8 mm ¦ 750 X 100 mm @ 4 sht | 22.608 | Kg | 48000 |  | 1085184
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9040 mm | 204.3763 | Kg | 48000 |  | 9810063.36
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 1150 mm @ 4 pcs | 259.992 | Kg | 48000 |  | 12479616
|  |  |  | - | Bracket bottom long. - TBHD 8/7 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 400 mm @ 3 pcs | 56.52 | Kg | 48000 |  | 2712960
|  |  |  | - | Bracket bottom long. - vertical stf. TBHD 8/9 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 500 mm @ 3 pcs | 70.65 | Kg | 48000 |  | 3391200
|  |  |  | - | Bracket bottom long - web bottom trans. ¦ Plate (A) thickness 10 mm ¦ 400 X 250 mm @ 4 sht | 37.68 | Kg | 48000 |  | 1808640
|  |  |  | - | Bracket chine long - web chine ¦ Plate (A) thickness 8 mm ¦ 550 X 300 mm @ 4 sht | 49.7376 | Kg | 48000 |  | 2387404.8
|  |  |  | - | Bracket chine long. - TBHD 8/7 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 500 mm | 23.55 | Kg | 48000 |  | 1130400
|  |  |  | - | Bracket chine long. - diagonal stf TBHD 8/9 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 500 mm | 23.55 | Kg | 48000 |  | 1130400
|  |  |  | - | Bracket side shell long. - TBHD 8/7 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 400 mm | 18.84 | Kg | 48000 |  | 904320
|  |  |  | - | Bracket side shell long. - TBHD 8/9 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 600 mm | 28.26 | Kg | 48000 |  | 1356480
|  |  |  | - | Stripping bracket chine ¦ Plate (A) thickness 8 mm ¦ 400 X 90 mm @ 4 sht | 10.8518 | Kg | 48000 |  | 520888.32
|  |  |  | - | Stripping bracket pillar ¦ Plate (A) thickness 8 mm ¦ 420 X 100 mm @ 4 sht | 12.6605 | Kg | 48000 |  | 607703.04
|  |  |  | - | Collar ¦ Plate (A) thickness 8 mm ¦ 180 X 80 mm @ 16 sht | 17.3629 | Kg | 48000 |  | 833421.312
|  | f |  | Tank 9 SB
|  |  |  | - | TBHD plate 9/8 ¦ Plate (A) thickness 8 mm ¦ 2250 X 750 mm | 105.975 | Kg | 48000 |  | 5086800
|  |  |  | - | TBHD plate 9/8 ¦ Plate (A) thickness 8 mm ¦ 400 X 450 mm | 13.5648 | Kg | 48000 |  | 651110.4
|  |  |  | - | Vertical stf TBHD 9/10 ¦ Angle bar size. 120 x 120 x 10 mm ¦ 910 mm | 20.5733 | Kg | 48000 |  | 987517.44
|  |  |  | - | Vertical stf TBHD 9/10 ¦ Angle bar size. 120 x 120 x 10 mm ¦ 760 mm | 17.1821 | Kg | 48000 |  | 824739.84
|  |  |  | - | Diagonal stf TBHD 9/10 ¦ Angle bar size. 120 x 120 x 10 mm ¦ 300 mm | 6.7824 | Kg | 48000 |  | 325555.2
|  |  |  | - | Bottom longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9040 mm @ 3 pcs | 613.129 | Kg | 48000 |  | 29430190.08
|  |  |  | - | Web bottom transverse ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 2050 mm @ 4 pcs | 463.464 | Kg | 48000 |  | 22246272
|  |  |  | - | Chine longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9040 mm | 204.3763 | Kg | 48000 |  | 9810063.36
|  |  |  | - | Web chine, Web ¦ Plate (A) thickness 8 mm ¦ 1430 X 650 mm @ 3 sht | 175.1178 | Kg | 48000 |  | 8405654.4
|  |  |  | - | Web chine, Web ¦ Plate (A) thickness 10 mm ¦ 1430 X 650 mm @ 1 sht | 72.9657 | Kg | 48000 |  | 3502356
|  |  |  | - | Web chine, Face ¦ Plate (A) thickness 8 mm ¦ 750 X 100 mm @ 4 sht | 22.608 | Kg | 48000 |  | 1085184
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9040 mm | 204.3763 | Kg | 48000 |  | 9810063.36
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 1160 mm @ 4 pcs | 262.2528 | Kg | 48000 |  | 12588134.4
|  |  |  | - | Bracket bottom long. - TBHD 9/10 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 500 mm @ 3 pcs | 70.65 | Kg | 48000 |  | 3391200
|  |  |  | - | Bracket bottom long. - vertical stf. TBHD 9/8 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 400 mm @ 3 pcs | 56.52 | Kg | 48000 |  | 2712960
|  |  |  | - | Bracket bottom long - web bottom trans. ¦ Plate (A) thickness 8 mm ¦ 400 X 250 mm @ 4 sht | 30.144 | Kg | 48000 |  | 1446912
|  |  |  | - | Bracket chine long - web chine ¦ Plate (A) thickness 8 mm ¦ 550 X 300 mm @ 4 sht | 49.7376 | Kg | 48000 |  | 2387404.8
|  |  |  | - | Bracket chine long. - TBHD 9/8 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 400 mm | 18.84 | Kg | 48000 |  | 904320
|  |  |  | - | Bracket chine long. - diagonal stf TBHD 9/10 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 400 mm | 18.84 | Kg | 48000 |  | 904320
|  |  |  | - | Bracket side shell long. - TBHD 9/8 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 420 mm | 19.782 | Kg | 48000 |  | 949536
|  |  |  | - | Bracket side shell long. - TBHD 9/10 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 630 mm | 29.673 | Kg | 48000 |  | 1424304
|  |  |  | - | Stripping bracket chine ¦ Plate (A) thickness 8 mm ¦ 400 X 90 mm @ 4 sht | 10.8518 | Kg | 48000 |  | 520888.32
|  |  |  | - | Stripping bracket pillar ¦ Plate (A) thickness 10 mm ¦ 400 X 90 mm @ 4 sht | 13.5648 | Kg | 48000 |  | 651110.4
|  |  |  | - | Collar ¦ Plate (A) thickness 8 mm ¦ 180 X 80 mm @ 16 sht | 17.3629 | Kg | 48000 |  | 833421.312
|  | g |  | Tank 10 SB
|  |  |  | - | TBHD plate 9/10 ¦ Plate (A) thickness 8 mm ¦ 1950 X 760 mm | 93.0696 | Kg | 48000 |  | 4467340.8
|  |  |  | - | Bottom longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 670 mm @ 3 pcs | 45.4421 | Kg | 48000 |  | 2181219.84
|  |  |  | - | Bracket bottom long. - TBHD 9/10 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 1060 mm @ 3 pcs | 149.778 | Kg | 48000 |  | 7189344
|  |  |  | - | Bracket bottom long. bottom - chine ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 640 mm @ 2 pcs | 60.288 | Kg | 48000 |  | 2893824
|  | h |  | Tank 8 PS
|  |  |  | - | Longitudinal sideshell ¦ Angle bar size. 120 x 120 x 10 mm ¦ 700 mm @ 2 pcs | 31.6512 | Kg | 48000 |  | 1519257.6
|  |  |  | - | Stringer ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 1140 mm | 64.4328 | Kg | 48000 |  | 3092774.4
[8 empty] | Total | 0 | 258145182.624
[9 empty] | Service | Material
Say :
Note : | [8 empty] | Balikpapan, 19 April 2025
1 |  |  | Cara pembayaran : | [5 empty] | PT. Meranti Nusa Bahari
Aditya Agung H.
General Manager
|  |  |  | - | Bracket longitudinal sideshell to vertikal stiffener ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 620 mm @ 2 pcs | 58.404 | Kg | 48000 |  | 2803392
|  |  |  | - | Bracket longitudinal sideshell to stringer ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 620 mm | 35.0424 | Kg | 48000 |  | 1682035.2
II |  |  | PERLENGKAPAN DECK
|  | a |  | Double bolder no 1 PS |  | 1 | Set | 16250000 |  | 16250000
|  |  |  | - | Body (existing material) ¦ Pipe seamless size. 10" Sch 80 ¦ 600 mm @ 2 pcs
|  |  |  | - | Holder arm (existing material) ¦ Roundbar size. 2" ¦ 600 mm @ 2 pcs
|  |  |  | - | Top (existing material) ¦ Plate (A) thickness 10 mm ¦ 400 X 400 mm @ 2 sht
|  |  |  | - | Fondation ¦ Plate (A) thickness 10 mm ¦ 1110 X 120 mm @ 2 sht
|  |  |  | - | Fondation ¦ Plate (A) thickness 10 mm ¦ 480 X 120 mm @ 2 sht
|  |  |  | - | Fondation ¦ Plate (A) thickness 10 mm ¦ 1100 X 450 mm
|  |  |  | - | Disassemble & reassemble double bolder (1 Set)
JR Rev. 01 Additional Work Req. by OS(06/03/25)
I |  |  | LAIN LAIN
|  | a |  | UT Flaw welding seam replating area |  | 1 | Ls | 10000000 | 10000000
[8 empty] | Total | 10000000 | 20735427.2
[8 empty] | Grand Total | 155255000 | 1631591618.624 | 1786846618.624
[9 empty] | Service | Material
Say :
Note : | [8 empty] | Balikpapan, 19 April 2025
1 |  |  | Cara pembayaran : | [5 empty] | PT. Meranti Nusa Bahari
Aditya Agung H.
General Manager

## Rincian Biaya rev.05
DETAIL OF DOCKING AND REPAIR COST
Rincian Biaya Docking Dan Perbaikan
Project Information
No |  |  |  | : 20/FIN/MKT-MNB/III/2025 |  |  |  | Name
Type |  |  |  | : All |  |  |  | Length | : 91.44 Meter
Client | [7 empty] | Breadth | : 24.38 Meter
Contact | [7 empty] | Depth | : 5.48 Meter
[8 empty] | Klass | : RINA
No |  |  | Item |  |  | Volume |  | Unit Price | Service | Material
I |  |  | PELAYANAN UMUM | [8 empty] | Luasan Painting
|  | a |  | Docking / Undocking |  | 1 | Ls | 23500000 | 23500000 |  |  | L | 26.98 | 242.82 | 242.82
|  | b |  | Asistensi naik/ turun dock, termasuk persiapan ganjal |  | 1 | Ls | 7000000 | 7000000 |  |  | B | 9 |  |  | #REF! | #REF! | #REF!
|  | c |  | Asistensi dengan mooring Boat |  | 1 | Ls | 5500000 | 5500000 |  |  | D | #REF! | 70
|  | d |  | Sewa dock selama tongkang dalam perbaikan (27 Februari 2025 - 25 Maret 2025) |  | 27 | Hari | 1600000 | 43200000 |  |  | Keliling | 71.96 |  | 19.66 | Panjang Sideboard
|  | e |  | Fasilitas sandar sesudah docking (sewa sandar) (26 Maret 2025 - 8 April 2025) |  | 5 | Hari | 400000 | 2000000 |  |  | Bottom | 197.82 |  | 7 | Lebar Sideboard
|  | f |  | Disediakan Tempat penyimpanan logistik selama perbaikan |  | 1 | Ls | 2000000 | 2000000 |  |  |  | #REF! | #REF! | #REF!
|  | g |  | Penggunaan alat angkat (<1 Ton) |  | 1 | Ls | 10000000 | 10000000 |  |  |  | #REF!
II |  |  | PERAWATAN BADAN KAPAL (Supplai Material by Owner)
|  | a |  | Sekrap Bagian Bawah Air |  | 2074 | m2 | 7000 | 14518000
|  | b |  | Sandblasting Bottom Sampai Waterline (S.A 2.0) |  | 2074 | m2 | 70000 | 145180000
|  | c |  | Sandblasting Top Side (S.A 2.0) |  | 1263 | m2 | 70000 | 88410000 |  |  | 1 | PELAYANAN UMUM
|  | d |  | Cuci Air Tawar |  | 1263 | m2 | 6500 | 8209500
|  | e |  | Sandblasting External Deck (S.A 2.0) |  | 682 | m2 | 70000 | 47740000
|  | f |  | Sandblasting External Sideboard (S.A 2.0) |  | 1151 | m2 | 70000 | 80570000
|  | f |  | Sandblasting winch House (S.A 2.0) |  | 65 | m2 | 70000 | 4550000
|  | g |  | Pengecatan Bagian Bawah Air (1x primer,1x sealer,1 xAF) |  | 2074 | m2 | 20500 | 42517000 |  |  | 2 | PERAWATAN LAMBUNG
|  | h |  | Pengecatan Top Side (1x primer,1x top coat) |  | 1263 | m2 | 14000 | 17682000 |  |  | 4 | SISTIM PENGGERAK
|  | i |  | Pengecetan eksternal deck (1x primer, 1x top coat) |  | 682 | m2 | 14000 | 9548000
|  | j |  | Pengecetan eksternal sideboard (1x primer, 1x top coat) |  | 1151 | m2 | 14000 | 16114000
|  | j |  | Pengecetan Winch House (1x primer, 1x top coat) |  | 65 | m2 | 14000 | 910000
|  | k |  | Pemasangan Zinc Anode |  | 62 | bh | 125000 | 7750000 |  |  | 14 | PERLENGKAPAN DECK
|  | l |  | Pengecatan Draft Mark, Nama Kapal |  | 1 | Ls | 1275000 | 1275000 |  |  | 15 | AKOMODASI
III |  |  | TANGKI - TANGKI
|  | a |  | Buka Manhole |  | 16 | pcs | 230000 | 3680000
|  | b |  | Dilakukan Freegas Sebelum Pemeriksaan Kedalam Tangki |  | 9 | Tank | 260000 | 2340000
|  | c |  | Air Test tangki |  | 11 | Tank | 1900000 | 20900000
IV |  |  | LAPORAN DAN GAMBAR
|  | a |  | Dibuatkan laporan pengedockan dan gambar bukaan kulit sesuai posisi replating |  | 1 | set | 2000000 | 2000000
JR Rev. 00 Initial Survey join with OS (28/02/25)
I |  |  | REPLATTING
| I.1 |  |  | BOTTOM
|  | a |  | Fr 5/6-6/7
|  |  |  | - | Lajur D/E SB ¦ Plate (ABS) thickness 12 mm ¦ 2050 X 1840 mm | 355.3224 | Kg | 33000 |  | 11725639.2
|  |  |  | - | Lajur E SB ¦ Plate (ABS) thickness 12 mm ¦ 2050 X 920 mm | 177.6612 | Kg | 33000 |  | 5862819.6
|  | b |  | Fr 6/7-9/10
|  |  |  | - | Lajur D/E SB ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 1840 mm | 1060.7674 | Kg | 33000 |  | 35005322.88
|  |  |  | - | Lajur E SB ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 920 mm | 530.3837 | Kg | 33000 |  | 17502661.44
|  | c |  | Fr 9/10-12/13
|  |  |  | - | Lajur D/E SB ¦ Plate (ABS) thickness 12 mm ¦ 6100 X 1840 mm | 1057.3008 | Kg | 33000 |  | 34890926.4
|  |  |  | - | Lajur E SB ¦ Plate (ABS) thickness 12 mm ¦ 6100 X 920 mm | 528.6504 | Kg | 33000 |  | 17445463.2
|  | d |  | Fr 12/13-15/16
|  |  |  | - | Lajur D/E SB ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 1840 mm | 1060.7674 | Kg | 33000 |  | 35005322.88
|  |  |  | - | Lajur E SB ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 920 mm | 530.3837 | Kg | 33000 |  | 17502661.44
|  | e |  | Fr 15/16-18/19
|  |  |  | - | Lajur D/E SB ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 1840 mm | 1060.7674 | Kg | 33000 |  | 35005322.88
|  |  |  | - | Lajur E SB ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 920 mm | 530.3837 | Kg | 33000 |  | 17502661.44
|  | f |  | Fr 18/19-20/21
|  |  |  | - | Lajur D SB ¦ Plate (ABS) thickness 12 mm ¦ 3550 X 730 mm | 244.1193 | Kg | 33000 |  | 8055936.9
[8 empty] | Total | 607093500 | 235504738.26 | 842598238.26 | [5 empty] | 102.15 | Panjang Sideboard
[9 empty] | Service | Material
Say : | [16 empty] | 26.04 | Lebar Sideboard
Note : | [8 empty] | Balikpapan, 11 Juni 2025
1 |  |  | Cara pembayaran : | [5 empty] | PT. Meranti Nusa Bahari
Aditya Agung H.
General Manager
|  | g |  | Fr 36/27-39/40
|  |  |  | - | Lajur E SB ¦ Plate (ABS) thickness 12 mm ¦ 6720 X 650 mm | 411.4656 | Kg | 33000 |  | 13578364.8
| I.2 |  |  | CHINE
|  | a |  | Fr 5/6-6/7 SB
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 2120 X 810 mm | 161.7602 | Kg | 33000 |  | 5338087.92
|  | b |  | Fr 6/7-10/11 SB
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 6130 X 810 mm | 467.7313 | Kg | 33000 |  | 15435131.58
|  | c |  | Fr 10/11-13/14 SB
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 810 mm | 466.9682 | Kg | 33000 |  | 15409951.92
|  | d |  | Fr 13/14-15/16 SB
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 3360 X 810 mm | 256.3747 | Kg | 33000 |  | 8460365.76
|  | e |  | Fr 15/16-18/19 SB
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 6020 X 810 mm | 459.338 | Kg | 33000 |  | 15158155.32
|  | f |  | Fr 18/19-22/23 SB
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 810 mm | 466.9682 | Kg | 33000 |  | 15409951.92
|  | g |  | Fr 5/6-22/23
|  |  |  | - | Lower chine ¦ Roundbar size. 2" ¦ 29560 mm | 564.3418 | Kg | 33000 |  | 18623278.872
|  |  |  | - | Upper chine ¦ Roundbar size. 2" ¦ 23900 mm | 456.2845 | Kg | 33000 |  | 15057387.18
|  | h |  | Fr 36/37-39/40
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 6110 X 500 mm | 345.3372 | Kg | 33000 |  | 11396127.6
|  |  |  | - | Lower chine ¦ Roundbar size. 2" ¦ 6010 mm | 114.7393 | Kg | 33000 |  | 3786397.362
| I.3 |  |  | SIDE SHELL
|  | a |  | Fr 5/6-8/9 SB
|  |  |  | - | Lajur G ¦ Plate (ABS) thickness 12 mm ¦ 5380 X 930 mm | 471.3203 | Kg | 33000 |  | 15553569.24
|  | b |  | Fr 8/9-12/13 SB
|  |  |  | - | Lajur G ¦ Plate (ABS) thickness 12 mm ¦ 6110 X 930 mm | 535.2727 | Kg | 33000 |  | 17663997.78
|  | c |  | Fr 12/13-15/16 SB
|  |  |  | - | Lajur G ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 930 mm | 536.1487 | Kg | 33000 |  | 17692907.76
|  | d |  | Fr 15/16-18/19 SB
|  |  |  | - | Lajur G ¦ Plate (ABS) thickness 12 mm ¦ 6120 X 930 mm | 536.1487 | Kg | 33000 |  | 17692907.76
|  | e |  | Fr 0/1-1/2 PS
|  |  |  | - | Lajur H ¦ Plate (ABS) thickness 12 mm ¦ 1100 X 1760 mm | 182.3712 | Kg | 33000 |  | 6018249.6
|  |  |  | - | Lajur H/I ¦ Plate (ABS) thickness 12 mm ¦ 1100 X 460 mm | 57.1982 | Kg | 33000 |  | 1887541.92
|  | f |  | Fr 1/2-4/5 PS
|  |  |  | - | Lajur G ¦ Plate (ABS) thickness 12 mm ¦ 3480 X 740 mm | 242.5838 | Kg | 33000 |  | 8005266.72
|  |  |  | - | Lajur G/H ¦ Plate (ABS) thickness 12 mm ¦ 6100 X 1540 mm | 884.9148 | Kg | 33000 |  | 29202188.4
|  |  |  | - | Lajur H/I ¦ Plate (ABS) thickness 12 mm ¦ 6100 X 1760 mm | 1011.3312 | Kg | 33000 |  | 33373929.6
|  | g |  | Fr 4/5-7/8 PS
|  |  |  | - | Lajur G ¦ Plate (ABS) thickness 12 mm ¦ 6100 X 740 mm | 425.2188 | Kg | 33000 |  | 14032220.4
|  |  |  | - | Lajur G/H ¦ Plate (ABS) thickness 12 mm ¦ 6100 X 1540 mm | 884.9148 | Kg | 33000 |  | 29202188.4
|  |  |  | - | Lajur H/I ¦ Plate (ABS) thickness 12 mm ¦ 6100 X 1760 mm | 1011.3312 | Kg | 33000 |  | 33373929.6
|  | h |  | Fr 7/8-10/11 PS
|  |  |  | - | Lajur G/H ¦ Plate (ABS) thickness 12 mm ¦ 6020 X 1830 mm | 1037.7637 | Kg | 33000 |  | 34246202.76
|  | i |  | Fr 0-7/8 PS
|  |  |  | - | Sheer strake (sideshell) ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 1860 mm | 87.606 | Kg | 33000 |  | 2890998
|  |  |  | - | Sheer strake (sideshell) ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 4830 mm | 227.493 | Kg | 33000 |  | 7507269
|  |  |  | - | Sheer strake (sideshell) ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 5360 mm | 252.456 | Kg | 33000 |  | 8331048
|  | j |  | Draft mark AP PS
|  |  |  | - | Letter 2,3,4,5,6,8 ¦ Plate (A) thickness 8 mm ¦ 100 X 80 mm @ 18 sht | 18 | Set | 100000 |  | 1800000
|  |  |  | - | Letter M ¦ Plate (A) thickness 8 mm ¦ 100 X 80 mm @ 4 sht | 4 | Set | 100000 |  | 400000
[8 empty] | Total | 0 | 416527615.174
[9 empty] | Service | Material
Say :
Note : | [8 empty] | Balikpapan, 11 Juni 2025
1 |  |  | Cara pembayaran : | [5 empty] | PT. Meranti Nusa Bahari
Aditya Agung H.
General Manager
|  | k |  | Draft mark AP SB
|  |  |  | - | Letter 2,4 ¦ Plate (A) thickness 8 mm ¦ 140 X 90 mm @ 2 sht | 2 | Set | 100000 |  | 200000
| I.4 |  |  | CORNER
|  | a |  | Corner AP
|  |  |  | - | Corner PS ¦ Plate (ABS) thickness 12 mm ¦ 2040 X 1800 mm | 345.9024 | Kg | 33000 |  | 11414779.2
|  |  |  | - | Sheer strake ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 4250 mm | 200.175 | Kg | 33000 |  | 6605775
| I.5 |  |  | MAIN DECK
|  | a |  | Fr 0-1/2 PS
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 3580 X 940 mm | 317.0018 | Kg | 33000 |  | 10461060.72
|  | b |  | Fr 1/2-3/4 PS
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 4420 X 940 mm | 391.3822 | Kg | 33000 |  | 12915611.28
| I.6 |  |  | SIDEBOARD
|  | a |  | Sideboard stantion PS
|  |  |  | - | St 1 , web ¦ Plate (A) thickness 10 mm ¦ 600 X 350 mm | 19.782 | Kg | 30500 |  | 603351
|  |  |  | - | St 1 , face ¦ Plate (A) thickness 10 mm ¦ 350 X 100 mm | 3.297 | Kg | 30500 |  | 100558.5
|  |  |  | - | St 2 , web ¦ Plate (A) thickness 10 mm ¦ 600 X 350 mm | 19.782 | Kg | 30500 |  | 603351
|  |  |  | - | St 2 , face ¦ Plate (A) thickness 10 mm ¦ 350 X 100 mm | 3.297 | Kg | 30500 |  | 100558.5
|  |  |  | - | St 3 , web ¦ Plate (A) thickness 10 mm ¦ 600 X 350 mm | 19.782 | Kg | 30500 |  | 603351
|  |  |  | - | St 3 , face ¦ Plate (A) thickness 10 mm ¦ 350 X 100 mm | 3.297 | Kg | 30500 |  | 100558.5
|  |  |  | - | Baseplate ¦ Plate (A) thickness 10 mm ¦ 620 X 70 mm @ 3 sht | 12.2648 | Kg | 30500 |  | 374077.62
| I.8 |  |  | INTERNAL TANK
|  | a |  | Tank 10 PS
|  |  |  | - | TBHD plate ¦ Plate (A) thickness 8 mm ¦ 4150 X 1190 mm | 310.1378 | Kg | 33000 |  | 10234547.4
|  |  |  | - | Ordinary chine ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 750 mm | 35.325 | Kg | 33000 |  | 1165725
|  |  |  | - | Web chine, Web ¦ Plate (A) thickness 10 mm ¦ 500 X 330 mm | 15.543 | Kg | 33000 |  | 512919
|  |  |  | - | Web chine, Web ¦ Plate (A) thickness 10 mm ¦ 500 X 300 mm | 14.13 | Kg | 33000 |  | 466290
|  |  |  | - | Web chine, Face ¦ Plate (A) thickness 10 mm ¦ 190 X 130 mm | 2.3267 | Kg | 33000 |  | 76782.42
|  |  |  | - | Web chine, Face ¦ Plate (A) thickness 10 mm ¦ 120 X 120 mm | 1.3565 | Kg | 33000 |  | 44763.84
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 2980 mm | 67.3718 | Kg | 33000 |  | 2223270.72
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 4820 mm | 108.9706 | Kg | 33000 |  | 3596028.48
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 6130 mm | 138.587 | Kg | 33000 |  | 4573372.32
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 7350 mm | 166.1688 | Kg | 33000 |  | 5483570.4
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 8540 mm | 193.0723 | Kg | 33000 |  | 6371386.56
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9840 mm | 222.4627 | Kg | 33000 |  | 7341269.76
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 430 mm | 9.7214 | Kg | 33000 |  | 320807.52
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 460 mm | 10.3997 | Kg | 33000 |  | 343189.44
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 1280 mm | 28.9382 | Kg | 33000 |  | 954961.92
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 770 mm | 17.4082 | Kg | 33000 |  | 574469.28
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 1180 mm | 26.6774 | Kg | 33000 |  | 880355.52
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 670 mm | 15.1474 | Kg | 33000 |  | 499862.88
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 1030 mm | 23.2862 | Kg | 33000 |  | 768445.92
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 1130 mm | 25.547 | Kg | 33000 |  | 843052.32
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 880 mm | 19.895 | Kg | 33000 |  | 656536.32
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 950 mm | 21.4776 | Kg | 33000 |  | 708760.8
|  |  |  | - | Frame ¦ Angle bar size. 120 x 120 x 10 mm ¦ 770 mm | 17.4082 | Kg | 33000 |  | 574469.28
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 3570 mm | 201.7764 | Kg | 33000 |  | 6658621.2
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 3480 mm | 196.6896 | Kg | 33000 |  | 6490756.8
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 2930 mm | 165.6036 | Kg | 33000 |  | 5464918.8
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 2170 mm | 122.6484 | Kg | 33000 |  | 4047397.2
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 1400 mm | 79.128 | Kg | 33000 |  | 2611224
[8 empty] | Total | 0 | 118570787.42
[9 empty] | Service | Material
Say :
Note : | [8 empty] | Balikpapan, 11 Juni 2025
1 |  |  | Cara pembayaran : | [5 empty] | PT. Meranti Nusa Bahari
Aditya Agung H.
General Manager
|  |  |  | - | Deck longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 7530 mm | 170.2382 | Kg | 33000 |  | 5617861.92
|  |  |  | - | Deck beam ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 1210 mm @ 5 pcs | 341.946 | Kg | 33000 |  | 11284218
|  |  |  | - | Bracket corner ¦ Plate (A) thickness 10 mm ¦ 920 X 400 mm | 34.6656 | Kg | 33000 |  | 1143964.8
|  |  |  | - | Bracket side shell long. - TBHD ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 420 mm @ 7 pcs | 138.474 | Kg | 33000 |  | 4569642
|  |  |  | - | Bracket side shell long. - web frame ¦ Plate (A) thickness 10 mm ¦ 400 X 250 mm @ 5 sht | 47.1 | Kg | 33000 |  | 1554300
|  |  |  | - | Collar ¦ Plate (A) thickness 8 mm ¦ 180 X 80 mm @ 14 sht | 15.1926 | Kg | 33000 |  | 501355.008
|  | b |  | Tank 9 PS
|  |  |  | - | TBHD plate 9/8 ¦ Plate (A) thickness 8 mm ¦ 1970 X 450 mm | 66.8066 | Kg | 33000 |  | 2204619.12
|  |  |  | - | TBHD horizontal stringer ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 3020 mm | 170.6904 | Kg | 33000 |  | 5632783.2
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9040 mm @ 2 pcs | 408.7526 | Kg | 33000 |  | 13488837.12
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 3970 mm @ 1 pcs | 89.7538 | Kg | 33000 |  | 2961874.08
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 8540 mm @ 1 pcs | 193.0723 | Kg | 33000 |  | 6371386.56
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 3480 mm @ 2 pcs | 157.3517 | Kg | 33000 |  | 5192605.44
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 2020 mm | 114.1704 | Kg | 33000 |  | 3767623.2
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 2060 mm | 116.4312 | Kg | 33000 |  | 3842229.6
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 2480 mm | 140.1696 | Kg | 33000 |  | 4625596.8
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 3600 mm | 203.472 | Kg | 33000 |  | 6714576
|  |  |  | - | Bracket side shell long. - stf TBHD 9/10 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 620 mm @ 5 pcs | 146.01 | Kg | 33000 |  | 4818330
|  |  |  | - | Bracket side shell long. - web frame ¦ Plate (A) thickness 10 mm ¦ 400 X 250 mm @ 3 sht | 28.26 | Kg | 33000 |  | 932580
|  |  |  | - | Bracket side shell long. - TBHD 9/8 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 400 mm @ 3 pcs | 56.52 | Kg | 33000 |  | 1865160
|  |  |  | - | Bracket side shell long. - side stringer ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 620 mm | 35.0424 | Kg | 33000 |  | 1156399.2
|  |  |  | - | Ladder holder bracket ¦ Plate (A) thickness 10 mm ¦ 200 X 90 mm @ 4 sht | 6.7824 | Kg | 33000 |  | 223819.2
|  |  |  | - | Collar ¦ Plate (A) thickness 8 mm ¦ 180 X 80 mm @ 3 sht | 3.2556 | Kg | 33000 |  | 107433.216
|  | c |  | Tank 6 SB
|  |  |  | - | Chine longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 1000 mm | 22.608 | Kg | 33000 |  | 746064
|  | d |  | Tank 7 SB
|  |  |  | - | TBHD plate 7/6 ¦ Plate (A) thickness 8 mm ¦ 840 X 300 mm | 18.9907 | Kg | 33000 |  | 626693.76
|  |  |  | - | Vertical stf TBHD 7/8 ¦ Angle bar size. 120 x 120 x 10 mm ¦ 780 mm | 17.6342 | Kg | 33000 |  | 581929.92
|  |  |  | - | Diagonal stf TBHD 7/8 ¦ Angle bar size. 120 x 120 x 10 mm ¦ 300 mm | 6.7824 | Kg | 33000 |  | 223819.2
|  |  |  | - | Bottom longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9040 mm | 204.3763 | Kg | 33000 |  | 6744418.56
|  |  |  | - | Bottom longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 7020 mm | 158.7082 | Kg | 33000 |  | 5237369.28
|  |  |  | - | Bottom longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 7140 mm | 161.4211 | Kg | 33000 |  | 5326896.96
|  |  |  | - | Web bottom transverse ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 2060 mm @ 3 pcs | 349.2936 | Kg | 33000 |  | 11526688.8
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 5790 mm | 130.9003 | Kg | 33000 |  | 4319710.56
|  |  |  | - | Chine longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9040 mm | 204.3763 | Kg | 33000 |  | 6744418.56
|  |  |  | - | Web chine, Web ¦ Plate (A) thickness 10 mm ¦ 1430 X 640 mm @ 3 sht | 215.5296 | Kg | 33000 |  | 7112476.8
|  |  |  | - | Web chine, Face ¦ Plate (A) thickness 10 mm ¦ 750 X 100 mm @ 3 sht | 21.195 | Kg | 33000 |  | 699435
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 1150 mm @ 2 pcs | 129.996 | Kg | 33000 |  | 4289868
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 1130 mm | 63.8676 | Kg | 33000 |  | 2107630.8
|  |  |  | - | Bracket bottom long. - TBHD 7/8 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 500 mm @ 3 pcs | 70.65 | Kg | 33000 |  | 2331450
|  |  |  | - | Bracket bottom long. - vertical stf. TBHD 7/6 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 500 mm | 23.55 | Kg | 33000 |  | 777150
|  |  |  | - | Bracket bottom long - web bottom trans. ¦ Plate (A) thickness 10 mm ¦ 400 X 250 mm @ 4 sht | 37.68 | Kg | 33000 |  | 1243440
|  |  |  | - | Bracket chine long - web chine ¦ Plate (A) thickness 8 mm ¦ 550 X 300 mm @ 3 sht | 37.3032 | Kg | 33000 |  | 1231005.6
|  |  |  | - | Bracket chine long. - TBHD 7/6 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 400 mm | 18.84 | Kg | 33000 |  | 621720
|  |  |  | - | Bracket chine long. - diagonal stf TBHD 7/8 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 400 mm | 18.84 | Kg | 33000 |  | 621720
|  |  |  | - | Bracket side shell long. - TBHD 7/8 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 600 mm | 28.26 | Kg | 33000 |  | 932580
|  |  |  | - | Stripping bracket chine ¦ Plate (A) thickness 8 mm ¦ 400 X 90 mm @ 3 sht | 8.1389 | Kg | 33000 |  | 268583.04
|  |  |  | - | Stripping bracket pillar ¦ Plate (A) thickness 8 mm ¦ 400 X 90 mm @ 3 sht | 8.1389 | Kg | 33000 |  | 268583.04
|  |  |  | - | Collar ¦ Plate (A) thickness 8 mm ¦ 180 X 80 mm @ 14 sht | 15.1926 | Kg | 33000 |  | 501355.008
|  |  |  | - | Ladder holder bracket ¦ Plate (A) thickness 8 mm ¦ 180 X 80 mm @ 2 sht | 2.1704 | Kg | 33000 |  | 71622.144
[8 empty] | Total | 0 | 153733823.496
[9 empty] | Service | Material
Say :
Note : | [8 empty] | Balikpapan, 11 Juni 2025
1 |  |  | Cara pembayaran : | [5 empty] | PT. Meranti Nusa Bahari
Aditya Agung H.
General Manager
|  | e |  | Tank 8 SB
|  |  |  | - | TBHD plate 8/7 ¦ Plate (A) thickness 8 mm ¦ 2030 X 760 mm | 96.8878 | Kg | 33000 |  | 3197298.72
|  |  |  | - | TBHD plate 8/7 ¦ Plate (A) thickness 8 mm ¦ 550 X 440 mm | 18.2371 | Kg | 33000 |  | 601824.96
|  |  |  | - | Sway ¦ H-beam size. 150 x 150 x 7 x 10 mm ¦ 410 mm | 15.498 | Kg | 33000 |  | 511434
|  |  |  | - | Vertical stf TBHD 8/9 ¦ Angle bar size. 120 x 120 x 10 mm ¦ 430 mm | 9.7214 | Kg | 33000 |  | 320807.52
|  |  |  | - | Vertical stf TBHD 8/9 ¦ Angle bar size. 120 x 120 x 10 mm ¦ 750 mm @ 2 pcs | 33.912 | Kg | 33000 |  | 1119096
|  |  |  | - | Diagonal stf TBHD 8/9 ¦ Angle bar size. 120 x 120 x 10 mm ¦ 600 mm | 13.5648 | Kg | 33000 |  | 447638.4
|  |  |  | - | Bottom longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9040 mm @ 3 pcs | 613.129 | Kg | 33000 |  | 20233255.68
|  |  |  | - | Web bottom transverse ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 2050 mm @ 4 pcs | 463.464 | Kg | 33000 |  | 15294312
|  |  |  | - | Chine longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9040 mm | 204.3763 | Kg | 33000 |  | 6744418.56
|  |  |  | - | Web chine, Web ¦ Plate (A) thickness 10 mm ¦ 1480 X 640 mm @ 4 sht | 297.4208 | Kg | 33000 |  | 9814886.4
|  |  |  | - | Web chine, Face ¦ Plate (A) thickness 8 mm ¦ 750 X 100 mm @ 4 sht | 22.608 | Kg | 33000 |  | 746064
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9040 mm | 204.3763 | Kg | 33000 |  | 6744418.56
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 1150 mm @ 4 pcs | 259.992 | Kg | 33000 |  | 8579736
|  |  |  | - | Bracket bottom long. - TBHD 8/7 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 400 mm @ 3 pcs | 56.52 | Kg | 33000 |  | 1865160
|  |  |  | - | Bracket bottom long. - vertical stf. TBHD 8/9 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 500 mm @ 3 pcs | 70.65 | Kg | 33000 |  | 2331450
|  |  |  | - | Bracket bottom long - web bottom trans. ¦ Plate (A) thickness 10 mm ¦ 400 X 250 mm @ 4 sht | 37.68 | Kg | 33000 |  | 1243440
|  |  |  | - | Bracket chine long - web chine ¦ Plate (A) thickness 8 mm ¦ 550 X 300 mm @ 4 sht | 49.7376 | Kg | 33000 |  | 1641340.8
|  |  |  | - | Bracket chine long. - TBHD 8/7 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 500 mm | 23.55 | Kg | 33000 |  | 777150
|  |  |  | - | Bracket chine long. - diagonal stf TBHD 8/9 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 500 mm | 23.55 | Kg | 33000 |  | 777150
|  |  |  | - | Bracket side shell long. - TBHD 8/7 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 400 mm | 18.84 | Kg | 33000 |  | 621720
|  |  |  | - | Bracket side shell long. - TBHD 8/9 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 600 mm | 28.26 | Kg | 33000 |  | 932580
|  |  |  | - | Stripping bracket chine ¦ Plate (A) thickness 8 mm ¦ 400 X 90 mm @ 4 sht | 10.8518 | Kg | 33000 |  | 358110.72
|  |  |  | - | Stripping bracket pillar ¦ Plate (A) thickness 8 mm ¦ 420 X 100 mm @ 4 sht | 12.6605 | Kg | 33000 |  | 417795.84
|  |  |  | - | Collar ¦ Plate (A) thickness 8 mm ¦ 180 X 80 mm @ 16 sht | 17.3629 | Kg | 33000 |  | 572977.152
|  | f |  | Tank 9 SB
|  |  |  | - | TBHD plate 9/8 ¦ Plate (A) thickness 8 mm ¦ 2250 X 750 mm | 105.975 | Kg | 33000 |  | 3497175
|  |  |  | - | TBHD plate 9/8 ¦ Plate (A) thickness 8 mm ¦ 400 X 450 mm | 13.5648 | Kg | 33000 |  | 447638.4
|  |  |  | - | Vertical stf TBHD 9/10 ¦ Angle bar size. 120 x 120 x 10 mm ¦ 910 mm | 20.5733 | Kg | 33000 |  | 678918.24
|  |  |  | - | Vertical stf TBHD 9/10 ¦ Angle bar size. 120 x 120 x 10 mm ¦ 760 mm | 17.1821 | Kg | 33000 |  | 567008.64
|  |  |  | - | Diagonal stf TBHD 9/10 ¦ Angle bar size. 120 x 120 x 10 mm ¦ 300 mm | 6.7824 | Kg | 33000 |  | 223819.2
|  |  |  | - | Bottom longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9040 mm @ 3 pcs | 613.129 | Kg | 33000 |  | 20233255.68
|  |  |  | - | Web bottom transverse ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 2050 mm @ 4 pcs | 463.464 | Kg | 33000 |  | 15294312
|  |  |  | - | Chine longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9040 mm | 204.3763 | Kg | 33000 |  | 6744418.56
|  |  |  | - | Web chine, Web ¦ Plate (A) thickness 8 mm ¦ 1430 X 650 mm @ 3 sht | 175.1178 | Kg | 33000 |  | 5778887.4
|  |  |  | - | Web chine, Web ¦ Plate (A) thickness 10 mm ¦ 1430 X 650 mm @ 1 sht | 72.9657 | Kg | 33000 |  | 2407869.75
|  |  |  | - | Web chine, Face ¦ Plate (A) thickness 8 mm ¦ 750 X 100 mm @ 4 sht | 22.608 | Kg | 33000 |  | 746064
|  |  |  | - | Side shell longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 9040 mm | 204.3763 | Kg | 33000 |  | 6744418.56
|  |  |  | - | Web frame ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 1160 mm @ 4 pcs | 262.2528 | Kg | 33000 |  | 8654342.4
|  |  |  | - | Bracket bottom long. - TBHD 9/10 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 500 mm @ 3 pcs | 70.65 | Kg | 33000 |  | 2331450
|  |  |  | - | Bracket bottom long. - vertical stf. TBHD 9/8 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 400 mm @ 3 pcs | 56.52 | Kg | 33000 |  | 1865160
|  |  |  | - | Bracket bottom long - web bottom trans. ¦ Plate (A) thickness 8 mm ¦ 400 X 250 mm @ 4 sht | 30.144 | Kg | 33000 |  | 994752
|  |  |  | - | Bracket chine long - web chine ¦ Plate (A) thickness 8 mm ¦ 550 X 300 mm @ 4 sht | 49.7376 | Kg | 33000 |  | 1641340.8
|  |  |  | - | Bracket chine long. - TBHD 9/8 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 400 mm | 18.84 | Kg | 33000 |  | 621720
|  |  |  | - | Bracket chine long. - diagonal stf TBHD 9/10 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 400 mm | 18.84 | Kg | 33000 |  | 621720
|  |  |  | - | Bracket side shell long. - TBHD 9/8 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 420 mm | 19.782 | Kg | 33000 |  | 652806
|  |  |  | - | Bracket side shell long. - TBHD 9/10 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 630 mm | 29.673 | Kg | 33000 |  | 979209
|  |  |  | - | Stripping bracket chine ¦ Plate (A) thickness 8 mm ¦ 400 X 90 mm @ 4 sht | 10.8518 | Kg | 33000 |  | 358110.72
|  |  |  | - | Stripping bracket pillar ¦ Plate (A) thickness 10 mm ¦ 400 X 90 mm @ 4 sht | 13.5648 | Kg | 33000 |  | 447638.4
|  |  |  | - | Collar ¦ Plate (A) thickness 8 mm ¦ 180 X 80 mm @ 16 sht | 17.3629 | Kg | 33000 |  | 572977.152
[8 empty] | Total | 0 | 168999077.214
[9 empty] | Service | Material
Say :
Note : | [8 empty] | Balikpapan, 11 Juni 2025
1 |  |  | Cara pembayaran : | [5 empty] | PT. Meranti Nusa Bahari
Aditya Agung H.
General Manager
|  | g |  | Tank 10 SB
|  |  |  | - | TBHD plate 9/10 ¦ Plate (A) thickness 8 mm ¦ 1950 X 760 mm | 93.0696 | Kg | 33000 |  | 3071296.8
|  |  |  | - | Bottom longitudinal ¦ Angle bar size. 120 x 120 x 10 mm ¦ 670 mm @ 3 pcs | 45.4421 | Kg | 33000 |  | 1499588.64
|  |  |  | - | Bracket bottom long. - TBHD 9/10 ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 1060 mm @ 3 pcs | 149.778 | Kg | 33000 |  | 4942674
|  |  |  | - | Bracket bottom long. bottom - chine ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 640 mm @ 2 pcs | 60.288 | Kg | 33000 |  | 1989504
|  | h |  | Tank 8 PS
|  |  |  | - | Longitudinal sideshell ¦ Angle bar size. 120 x 120 x 10 mm ¦ 700 mm @ 2 pcs | 31.6512 | Kg | 33000 |  | 1044489.6
|  |  |  | - | Stringer ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 1140 mm | 64.4328 | Kg | 33000 |  | 2126282.4
|  |  |  | - | Bracket longitudinal sideshell to vertikal stiffener ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 620 mm @ 2 pcs | 58.404 | Kg | 33000 |  | 1927332
|  |  |  | - | Bracket longitudinal sideshell to stringer ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 620 mm | 35.0424 | Kg | 33000 |  | 1156399.2
|  | i |  | Tank 1 PS
|  |  |  | - | Vertikal web ¦ Angle bar unequal size. 500 x 100 x 10 mm ¦ 870 mm | 49.1724 | Kg | 33000 |  | 1622689.2
|  |  |  | - | Vertikal, Web side ¦ Plate (A) thickness 10 mm ¦ 1260 X 180 mm | 21.3646 | Kg | 33000 |  | 705030.48
II |  |  | PERLENGKAPAN DECK
|  | a |  | Double bolder no 1 PS |  | 1 | Set | 16250000 |  | 16250000
|  |  |  | - | Body (existing material) ¦ Pipe seamless size. 10" Sch 80 ¦ 600 mm @ 2 pcs
|  |  |  | - | Holder arm (existing material) ¦ Roundbar size. 2" ¦ 600 mm @ 2 pcs
|  |  |  | - | Top (existing material) ¦ Plate (A) thickness 10 mm ¦ 400 X 400 mm @ 2 sht
|  |  |  | - | Fondation ¦ Plate (A) thickness 10 mm ¦ 1110 X 120 mm @ 2 sht
|  |  |  | - | Fondation ¦ Plate (A) thickness 10 mm ¦ 480 X 120 mm @ 2 sht
|  |  |  | - | Fondation ¦ Plate (A) thickness 10 mm ¦ 1100 X 450 mm
|  |  |  | - | Disassemble & reassemble double bolder (1 Set)
JR Rev. 01 Additional Work Req. by OS(06/03/25)
I |  |  | REPLATTING
| I.1 |  |  | CORNER
|  | a |  | Corner FP PS
|  |  |  | - | ¦ Plate (ABS) thickness 12 mm ¦ 3360 X 1200 mm | 379.8144 | Kg | 33000 |  | 12533875.2
|  |  |  | - | Sheer strake ¦ Angle bar unequal size. 350 x 100 x 10 mm ¦ 3600 mm | 169.56 | Kg | 33000 |  | 5595480
| I.2 |  |  | Chine
|  | a |  | Fr 49/50
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 1310 X 780 mm | 96.2536 | Kg | 33000 |  | 3176367.48
|  |  |  | - | Upper chine ¦ Roundbar size. 2" ¦ 1350 mm | 25.77 | Kg | 33000 |  | 850410
| I.3 |  |  | Main deck
|  | a |  | Fr 49/50
|  |  |  | - | Lajur F ¦ Plate (ABS) thickness 12 mm ¦ 1300 X 500 mm | 73.476 | Kg | 33000 |  | 2424708
| 1.4 |  |  | SIDEBOARD
|  | a |  | Stiffener sideboard SB
|  |  |  | - | ST. 9-10, stf 4 ¦ Angle bar size. 100 x 100 x 10 mm ¦ 1600 mm | 30.144 | Kg | 30500 |  | 919392
|  | b |  | Sideboard plate SB
|  |  |  | - | ST 9-10, stf 3-5 ¦ Plate (A) thickness 8 mm ¦ 900 X 900 mm | 50.868 | Kg | 30500 |  | 1551474
|  | c |  | Sideboard stantion SB
|  |  |  | - | Portable door frame FP PS, Stantion ¦ H-beam size. 200 x 200 x 8 x 12 mm ¦ 3630 mm | 217.3644 | Kg | 30500 |  | 6629614.2
|  |  |  | - | Portable door frame FP PS, Sway ¦ H-beam size. 200 x 200 x 8 x 12 mm ¦ 2410 mm | 144.3108 | Kg | 30500 |  | 4401479.4
|  |  |  | - | Portable door frame FP SB, inner ¦ Plate (A) thickness 12 mm ¦ 2080 X 100 mm | 23.5123 | Kg | 30500 |  | 717125.76
|  |  |  | - | Portable door frame FP SB, outer ¦ Plate (A) thickness 12 mm ¦ 1260 X 100 mm | 14.243 | Kg | 30500 |  | 434412.72
[8 empty] | Total | 0 | 75569625.08
[9 empty] | Service | Material
Say :
Note : | [8 empty] | Balikpapan, 11 Juni 2025
1 |  |  | Cara pembayaran : | [5 empty] | PT. Meranti Nusa Bahari
Aditya Agung H.
General Manager
II |  |  | TANGKI-TANGKI
|  | a |  | Manhole Tank 1 PS |  | 1 | Set | 4500000 |  | 4500000
|  |  |  | - | Cover ¦ Plate (A) thickness 10 mm ¦ 730 X 530 mm
|  |  |  | - | Handle ¦ Roundbar size. 3/4" ¦ 400 mm @ 2 pcs
|  |  |  | - | Handle ¦ Halfed chain galvanized size. 5/8" @ 2 pcs
|  |  |  | - | ¦ B/N SS size. 3/4" X 2 1/2" @ 24 Pcs
|  | b |  | Manhole Tank 1 CT-PS |  | 1 | Set | 4500000 |  | 4500000
|  |  |  | - | Cover ¦ Plate (A) thickness 10 mm ¦ 730 X 530 mm
|  |  |  | - | Handle ¦ Roundbar size. 3/4" ¦ 400 mm @ 2 pcs
|  |  |  | - | Handle ¦ Halfed chain galvanized size. 5/8" @ 2 pcs
|  |  |  | - | ¦ B/N SS size. 3/4" X 2 1/2" @ 24 Pcs
|  | c |  | Manhole Tank 6 CT-SB
|  |  |  | - | ¦ B/N SS size. 3/4" X 2 1/2" | 24 | pcs | 75000 |  | 1800000
III |  |  | PERLENGKAPAN DECK
|  | a |  | Double bolder no 5 PS
|  |  |  | - | Holder arm ¦ Roundbar size. 2" ¦ 570 mm | 10.8821 | Kg | 30500 |  | 331903.989
|  | b |  | Railing winch house ladder |  | 7 | joint | 200000 | 1400000
|  |  |  | - | ¦ Pipe seamless size. 2" Sch 40 | 1470 | mm | 393 |  | 577710
|  |  |  | - | ¦ Pipe seamless size. 2" Sch 40 | 1350 | mm | 393 |  | 530550
|  |  |  | - | ¦ Pipe seamless size. 2" Sch 40 | 1500 | mm | 393 |  | 589500
|  |  |  | - | Railing pillar ¦ Pipe seamless size. 2" Sch 40 | 1010 | mm | 393 |  | 396930
|  | c |  | Pad eye |  | 40 | set | 300000 |  | 12000000
|  |  |  | - | Pad eye for hull tire fender ¦ Plate (A) thickness 12 mm ¦ 130 X 80 mm @ 21 sht
|  |  |  | - | Baseplate ¦ Plate (A) thickness 12 mm ¦ 130 X 50 mm @ 1 sht
|  |  |  | - | Pad eye for push pad tire fender ¦ Plate (A) thickness 12 mm ¦ 150 X 70 mm @ 16 sht
IV |  |  | LAIN LAIN
|  | a |  | Open and close sideboard door FP |  | 1 | Ls | 2000000 | 2000000
|  | b |  | Install daprah pushtug, Daprah double (8 pcs) |  | 1 | Ls | 4000000 | 4000000
|  | c |  | Take down rampdoor extension at cargo room |  | 2 | pcs | 5000000 | 10000000
|  | d |  | Take down portable sidedoor at cargo room |  | 2 | pcs | 1500000 | 3000000
|  | e |  | Raise and take down portable sidedoor at outside deck FP |  | 2 | pcs | 1500000 | 3000000
|  | f |  | Raise and take down extension rampdoor at outside deck FP |  | 2 | pcs | 5000000 | 10000000
|  | g |  | Assist Raise and take down extension rampdoor at outside deck FP |  | 1 | Ls | 5000000 | 5000000
|  | h |  | UT Flaw welding seam replating area |  | 1 | Ls | 12500000 | 12500000
[8 empty] | Total | 50900000 | 25226593.989
[8 empty] | Grand Total | 657993500 | 1194132260.633 | 1852125760.633 | 185212576.0633 | 1666913184.5697
[8 empty] | Discount | 185212576.0633 | 0
[8 empty] | Grand Total After Discount | 472780923.9367 | 1194132260.633 | 1666913184.5697
[9 empty] | Service | Material
Say :
Note : | [8 empty] | Balikpapan, 11 Juni 2025
1 |  |  | Cara pembayaran : | [5 empty] | PT. Meranti Nusa Bahari
Aditya Agung H.
General Manager